## Sheet1
Defect ID | Test Case ID | Module | Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Screenshot | Severity | Priority | Status | Reported By
Bug_01 | TC_03 | Register | First Name field validation for blank input | On the Registration page, the First Name field should not allow blank input and must display the error message: “First Name is required.” | 1. Open the website. 2. Go to the Registration page. 3. Leave the First Name field blank. 4. Click Submit 5. Observe the error message. | “First Name is required.” | “First Name must be between 1 and 32 characters.” | TC_03 Screenshot | Major | High | New | Samiksha Balgude
Bug_02 | TC_04 | Register | Last Name field validation for blank input | On the Registration page, the Last Name field should not allow blank input and must display the error message: “Last Name is required.” | 1. Open the website. 2. Go to the Registration page. 3. Leave the Last Name field blank. 4. Click Submit. 5. Observe the error message. | “Last Name is required.” | “Last Name must be between 1 and 32 characters.” | TC_04 Screenshot | Major | High | New | Samiksha Balgude
Bug_03 | TC_06 | Register | Password field validation for blank input | On the Registration page, the Password field should not allow blank input and must display the error message: “Password is required.” | 1. Open the website. 2. Go to the Registration page. 3. Leave the Password field blank. 4. Fill other fields correctly. 5. Click Submit. 6. Observe the error message. | “Password is required.” | “Password must be between 4 and 20 characters.” | TC_06 Screenshot | Major | High | New | Samiksha Balgude
Bug_04 | TC_17 | Login | Error message for empty login fields | On the Login page, when all fields are left empty and the user clicks “Login,” the system should display an error message: “Fields required.” | 1. Open the website. 2. Click the “Login” button without entering any details. 3. Observe the error message. | “Fields required” | “Forgotten Password” message displayed. | TC_17 Screenshot | Major | High | New | Samiksha Balgude
Bug_05 | TC_19 | Login | Email format validation | On the Login page, the system should validate the email field and not allow invalid email formats (e.g., “user@domain”). The error message should be: “Invalid email format.” | 1. Open the website. 2. Enter an invalid email format (e.g., “user@domain”). 3. Enter any password. 4. Click “Login.” 5. Observe the error message. | “Invalid email format.” Login should not proceed. | “No match for Email address and/or Password.” | TC_21 Screenshot | Major | High | New | Samiksha Balgude
Bug_06 | TC_21 | Login | Password field validation for invalid characters | On the Login page, the Password field should reject disallowed characters or invalid symbols and display the error message: “Password format invalid.” | 1. Open the website. 2. Enter invalid characters in the Password field. 3. Click “Login.” 4. Observe the error message. | “Password format invalid.” Login should not proceed. | “No match for Email address and/or Password.” | TC_21 Screenshot | Major | High | New | Samiksha Balgude
Bug_07 | TC_55 | Checkout | Shipping options not displayed | On checkout page, multiple shipping options are expected but not shown. | 1. Open website. 2. Log in with valid credentials. 3. Add a product to the cart. 4. Proceed to checkout. 5. Enter personal details and shipping address .6. Check “Privacy Policy” and “Newsletter Subscription.” 7. Click “Continue.” 8. Select a shipping address. 9. Choose Shipping Method. | Multiple shipping options displayed. | Only one or no shipping option is shown. | TC_55 Screenshot | Major | High | New | Samiksha Balgude
Bug_08 | TC_56 | Checkout | Shipping options unavailable text | Shipping method selection does not reflect all available options. | 1. Open website. 2. Log in with valid credentials. 3. Add a product to the cart. 4. Proceed to checkout. 5. Enter personal details and shipping address. 6. Check “Privacy Policy” and “Newsletter Subscription.” 7. Click “Continue.” 8. Select a shipping address. 9. Choose Payment Method. | Multiple shipping options available. | Only standard shipping is visible. | TC_56 Screenshot | Major | Medium | New | Samiksha Balgude