## Sheet1
Req ID | Module | Functional Requirement Description | Test Case ID(s) Coverage | Total TCs | Final Execution Status | Notes / Defect ID
R-001 | Registration | System must handle registration and display correct field validation errors. | TC_01 to TC_14 | 14 | Failed | Failed validation tests linked to Bug_01, Bug_02, Bug_03.
R-002 | Login | Users must be able to log in securely with valid credentials. | TC_15 to TC_24 | 10 | Failed | Failed login validation tests linked to Bug_04, Bug_05, Bug_06.
R-003 | Categories | All product categories must link correctly to relevant product pages. | TC_25 to TC_33 | 9 | Passed | All TCs passed.
R-004 | Products & Cart | Add to Cart, view cart, remove, and data persistence must be functional. | TC_34 to TC_43 | 10 | Passed | All TCs passed.
R-005 | Checkout | Complete checkout, shipping, and payment selection flow must be functional. | TC_44 to TC_58 | 15 | Failed | Missing shipping/payment options, linked to Bug_07, Bug_08.
R-006 | Contact Us | Contact Us form must validate and submit successfully. | TC_59 to TC_65 | 7 | Passed | All TCs passed.